## data
site¦fix00012¦4188808420049567786¦2477626672974883536 | site¦fix00015 | du¦du_code | site¦region_name | site¦fix00008 | site¦fix00013 | site¦fix00010 | docata¦ZDCSZ640306 | docata¦ZDCSZ00843884 | docata¦ZDCSZ640230 | docata¦ZDCSZ00843885 | docata¦ZDCSZ0673674 | docata¦ZDCSZ00836966 | docata¦ZDCSZ640228 | docata¦ZDCSZ00885806 | docata¦ZDCSZ640229 | docata¦ZDCSZ0656912 | docata¦ZDCSZ0669212 | docata¦ZDCSZ00815531 | docata¦ZDCSZ00815532 | docata¦ZDCSZ642123 | docata¦ZDCSZ00969593 | docata¦ZDCSZ00969594 | docata¦ZDCSZ00969581 | docata¦ZDCSZ00969580 | docata¦ZDCSZ00969576 | docata¦ZDCSZ00969578 | docata¦ZDCSZ00969579 | docata¦ZDCSZ0657770 | docata¦ZDCSZ641766 | docata¦ZDCSZ0657771 | docata¦ZDCSZ641765 | WP10400¦plan_end_date | WP10400¦actual_end_date | WP10400¦status | WP10400¦AC0000111560¦plan_start_date | WP10400¦AC0000111560¦plan_end_date | WP10400¦AC0000111560¦actual_start_date | WP10400¦AC0000111560¦actual_end_date | WP10400¦AC0000111560¦responsible_user | WP10400¦AC0000111560¦responsible_team | WP10400¦AC0000111560¦supplier_no | WP10400¦AC0000111560¦comp_percent | WP10400¦AC0000111560¦assign_flag | WP10400¦AC0000111560¦status | WP10400¦AC0000111560¦remark | WP10400¦AC0000111561¦plan_start_date | WP10400¦AC0000111561¦plan_end_date | WP10400¦AC0000111561¦actual_start_date | WP10400¦AC0000111561¦actual_end_date | WP10400¦AC0000111561¦responsible_user | WP10400¦AC0000111561¦responsible_team | WP10400¦AC0000111561¦supplier_no | WP10400¦AC0000111561¦comp_percent | WP10400¦AC0000111561¦assign_flag | WP10400¦AC0000111561¦status | WP10400¦AC0000111561¦remark | WP10400¦AC0000111563¦plan_start_date | WP10400¦AC0000111563¦plan_end_date | WP10400¦AC0000111563¦actual_start_date | WP10400¦AC0000111563¦actual_end_date | WP10400¦AC0000111563¦responsible_user | WP10400¦AC0000111563¦responsible_team | WP10400¦AC0000111563¦supplier_no | WP10400¦AC0000111563¦comp_percent | WP10400¦AC0000111563¦assign_flag | WP10400¦AC0000111563¦status | WP10400¦AC0000111563¦remark | WP10400¦AC0000111564¦plan_start_date | WP10400¦AC0000111564¦plan_end_date | WP10400¦AC0000111564¦actual_start_date | WP10400¦AC0000111564¦actual_end_date | WP10400¦AC0000111564¦responsible_user | WP10400¦AC0000111564¦responsible_team | WP10400¦AC0000111564¦supplier_no | WP10400¦AC0000111564¦comp_percent | WP10400¦AC0000111564¦assign_flag | WP10400¦AC0000111564¦status | WP10400¦AC0000111564¦doc_delivery_status | WP10400¦AC0000111564¦remark | docata¦ZDCSZ640254 | docata¦ZDCSZ640255 | WP11000¦plan_end_date | WP11000¦actual_end_date | WP11000¦status | WP11000¦AC0000111565¦plan_start_date | WP11000¦AC0000111565¦plan_end_date | WP11000¦AC0000111565¦actual_start_date | WP11000¦AC0000111565¦actual_end_date | WP11000¦AC0000111565¦responsible_user | WP11000¦AC0000111565¦responsible_team | WP11000¦AC0000111565¦supplier_no | WP11000¦AC0000111565¦comp_percent | WP11000¦AC0000111565¦assign_flag | WP11000¦AC0000111565¦status | WP11000¦AC0000111565¦remark | WP10500¦AC0000111566¦plan_start_date | WP10500¦AC0000111566¦plan_end_date | WP10500¦AC0000111566¦actual_start_date | WP10500¦AC0000111566¦actual_end_date | WP10500¦AC0000111566¦responsible_user | WP10500¦AC0000111566¦responsible_team | WP11100¦AC0000111567¦plan_start_date | WP11100¦AC0000111567¦plan_end_date | WP11100¦AC0000111567¦actual_start_date | WP11100¦AC0000111567¦actual_end_date | WP11100¦AC0000111567¦responsible_user | WP11100¦AC0000111567¦responsible_team | WP11400¦AC0000111569¦plan_start_date | WP11400¦AC0000111569¦plan_end_date | WP11400¦AC0000111569¦actual_start_date | WP11400¦AC0000111569¦actual_end_date | WP11400¦AC0000111569¦responsible_user | WP11400¦AC0000111569¦responsible_team | docata¦ZDCSZ00885808 | WPC000011222¦AC0000111592¦plan_start_date | WPC000011222¦AC0000111592¦plan_end_date | WPC000011222¦AC0000111592¦actual_start_date | WPC000011222¦AC0000111592¦actual_end_date | WPC000011222¦AC0000111592¦responsible_user | WPC000011222¦AC0000111594¦plan_start_date | WPC000011222¦AC0000111594¦plan_end_date | WPC000011222¦AC0000111594¦actual_start_date | WPC000011222¦AC0000111594¦actual_end_date | WP11200¦AC0000111568¦plan_start_date | WP11200¦AC0000111568¦plan_end_date | WP11200¦AC0000111568¦actual_start_date | WP11200¦AC0000111568¦actual_end_date | WP11200¦AC0000111568¦responsible_user | WP11200¦AC0000111568¦responsible_team | WP12000¦AC0000111579¦plan_start_date | WP12000¦AC0000111579¦plan_end_date | WP12000¦AC0000111579¦actual_start_date | WP12000¦AC0000111579¦actual_end_date | WP12000¦AC0000111579¦responsible_user | docata¦ZDCSZ01027586 | docata¦ZDCSZ01027605 | WPC000013914¦AC0000157841¦plan_start_date | WPC000013914¦AC0000157841¦plan_end_date | WPC000013914¦AC0000157841¦actual_start_date | WPC000013914¦AC0000157841¦actual_end_date | WPC000013914¦AC0000157841¦responsible_user
Site Basic Info | Site Basic Info | Du | Site Basic Info | Site Basic Info | Site Basic Info | Site Basic Info | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | Installation | TX Solution | Network Planning | Network Planning | Network Planning | Network Planning | Network Planning | Network Planning | Network Planning | Installation | Installation | Installation | Installation | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Survey&Design | Installation | Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Ready For Installation | Material On Site | Material On Site | Material On Site | Material On Site | Material On Site | Material On Site | Telecom Installation | Telecom Installation | Telecom Installation | Telecom Installation | Telecom Installation | Telecom Installation | Software Commissioning | Software Commissioning | Software Commissioning | Software Commissioning | Software Commissioning | Software Commissioning | Installation | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Q&EHS | Hardware Dismantling | Hardware Dismantling | Hardware Dismantling | Hardware Dismantling | Hardware Dismantling | Hardware Dismantling | (Preliminary/Provisional) Acceptance Certification | (Preliminary/Provisional) Acceptance Certification | (Preliminary/Provisional) Acceptance Certification | (Preliminary/Provisional) Acceptance Certification | (Preliminary/Provisional) Acceptance Certification | Network Planning | Network Planning | TX Planning | TX Planning | TX Planning | TX Planning | TX Planning
Site Basic Info | Site Basic Info | Du | Site Basic Info | Site Basic Info | Site Basic Info | Site Basic Info | Wireless RAN | Microwave | Wireless RAN | Microwave | Wireless RAN | Wireless RAN | Wireless RAN | Microwave | Wireless RAN | Wireless RAN | Wireless RAN | Microwave | Microwave | TX SOW Details | Microwave | Microwave | Microwave | Microwave | Microwave | Microwave | Microwave | Wireless RAN | Wireless RAN | Wireless RAN | Wireless RAN | Survey&Design | Survey&Design | Survey&Design | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | Physical Survey | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to ZTE | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR Submitted to Customer | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | TSSR customer Approval | Wireless RAN | Wireless RAN | Ready For Installation | Ready For Installation | Ready For Installation | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material Collection | Material On Site | Material On Site | Material On Site | Material On Site | Material On Site | Material On Site | Equipment Installation | Equipment Installation | Equipment Installation | Equipment Installation | Equipment Installation | Equipment Installation | TX Integrated | TX Integrated | TX Integrated | TX Integrated | TX Integrated | TX Integrated | Microwave | L1 Approved | L1 Approved | L1 Approved | L1 Approved | L1 Approved | EHS Check | EHS Check | EHS Check | EHS Check | MRCF | MRCF | MRCF | MRCF | MRCF | MRCF | PAC Approved | PAC Approved | PAC Approved | PAC Approved | PAC Approved | Microwave | Microwave | TX Planning | TX Planning | TX Planning | TX Planning | TX Planning
customer site code | customer site name | du code | region | Province/State | Latitude (North Plus South Minus) | Longitude (East Plus West Minus) | Plan Week - TSS | Plan Month - TSS | Plan Week - TI | Plan Month - TI | Issue Tagging | Issue Tagging Details | Current issue Owner | TX Current Issue Status Tagging | Current issue Remarks | TX Upgrade Scope | Wireless RAN TX Acceptance Scope | BOQ Configuration | Tx SOW | TX SOW Details | NE SOW Details | FE SOW Details | MW Config ODU Type | MW Config Antenna Type | MW Config MW Frequency | MW Config Antenna Size NE | MW Config Antenna Size FE | SubCon - TSS Team | Subcon PR - TSS | SubCon - TI Team | Subcon PR - TI | planned end time | actual end time | status | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | remark | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | remark | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | remark | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | doc delivery status | remark | DO Number | DO Remark | planned end time | actual end time | status | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | responsible company | complete percent | assign status | activity status | remark | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | TX Cutover Date | planned start time | planned end time | actual start time | actual end time | responsible person | planned start time | planned end time | actual start time | actual end time | planned start time | planned end time | actual start time | actual end time | responsible person | responsible team | planned start time | planned end time | actual start time | actual end time | responsible person | Subcon - Planning | Subcon PR - Planning | planned start time | planned end time | actual start time | actual end time | responsible person
4008B_AD | Farlim | DU00005252305 | Northern | Penang | 5.3959 | 100.2892 | [7 empty] | 03. TSS Only | 8/9: TSS only, request change DU. 21/8: TSS done, Pending MSP/GOP for FE confirmation. 23/07: TSS Done, Pending SOW 24/07: DO Done | TSS |  | 23G_2+0_56M NE_4008B New 23G_DP_1.2M(MS) x1. Re-use exsiting RTN910A(RTN01). New XMC_3E, Sub A&B_Lo x2. FE_P00062 New 23G_DP_1.2M(MS) x1. New RTN910A(RTN01). New XMC_3E, Sub A&B_Hi x2. New CAT6 Cable with suitable length x1. | MW New Link / Reroute | Existing HW MW Link 23G_1+0_56M_512QAM_450M. Install new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B. NE_4008B 1.Install new 23G_DP_1.2M(MS) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Lo. Configure it. 4.Build new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. 5.Request new xC Vlan DCN & new Vlan services from ZTE IPRAN Team. 6.Migrate RAN Traffic to new MW Link 23G_2+0_56M_512QAM_900M_EPLA. 7.Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. FE_P00062 1.Install new 23G_DP_1.2M(MS) x1. 2.Install new RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Enable new electrical 1G port at PTN/Cisco. Request from ZTE IPRAN Team. 6.Patching port 8-EM6-1 of new RTN910A(RTN01) and new electrical 1G port at PTN/Cisco. 7.Migrate RAN Traffic via xC PTN/Cisco. 8.Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. | Existing HW MW Link 23G_1+0_56M_512QAM_450M. Install new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B. NE_4008B 1.Install new 23G_DP_1.2M(MS) x1. 2.Re-use existing RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Lo. Configure it. 4.Build new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. 5.Request new xC Vlan DCN & new Vlan services from ZTE IPRAN Team. 6.Migrate RAN Traffic to new MW Link 23G_2+0_56M_512QAM_900M_EPLA. 7.Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. | Existing HW MW Link 23G_1+0_56M_512QAM_450M. Install new HW MW Link 23G_2+0_56M_512QAM_900M_EPLA. Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. Site Impacted : 4008B. FE_P00062 1.Install new 23G_DP_1.2M(MS) x1. 2.Install new RTN910A(RTN01). 3.Install new 2x XMC_3E, Sub A&B_Hi. Configure it. 4.Enable port 8-EM6-1 of new RTN910A(RTN01). 5.Enable new electrical 1G port at PTN/Cisco. Request from ZTE IPRAN Team. 6.Patching port 8-EM6-1 of new RTN910A(RTN01) and new electrical 1G port at PTN/Cisco. 7.Migrate RAN Traffic via xC PTN/Cisco. 8.Later, decom existing HW MW Link 23G_1+0_56M_512QAM_450M. | XMC_3E | MS | 23G | 23G_DP_1.2M(MS) x1 | 23G_DP_1.2M(MS) x1 | GTSB | SQ202506180613-GTSB | GTSB | No PR required-Work at TSS only | 2025-09-29 | 2025-09-23 | Completed | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 |  | Girobumi Technologies SDN. BHD. | 1 | Unassigned | Completed |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1 | Assigned | Completed |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1 | Unassigned | Completed |  | 2025-09-22 | 2025-09-29 | 2025-09-22 | 2025-09-23 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1 | Assigned | Completed | Closed |  | DOWMY25072403 |  | 2025-07-25 | 2025-08-09 | Completed | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-08-09 | ZHANG DONG6000003031 | Design and Material Team | DCH Technology SDN.BHD | 1 | Assigned | Completed |  | 2025-08-19 | 2025-08-31 | 2025-08-19 | 2025-10-13 | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | 2025-08-19 | 2025-08-31 | 2025-08-19 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | GTSB TI | [7 empty] | 2025-08-19 | 2025-08-31 | 2025-08-19 |  | MUHAMAD HAZIQ//BIN MOHD HASAZLI/6000034995 | 2025-08-19 | 2025-08-31 | 2025-08-19 | [12 empty] | GTSB | SQ202505070167-GTSB | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | HSU//MYET CHAE/6799000011
A01073_AD | BDR_UNI_LAKEVILLE | DU00005283921 | Northern | Perak | 4.3532 | 100.9922 | [7 empty] | 00. Integrated/RFS Done |  | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | IF cable | MW Swap | MW SWAP A01073-A00607 WITH 18G_2+0_0.6/1.2_DP XMC-3E SB A,B. DISMANTLE AND REINSTALL AT NEW ANTENNA PLACE. MODULATION ISSUE IN CURRENT EXISITING LINK_RUNNING QPSK ONLY. | MW SWAP A01073-A00607 WITH 18G_2+0_0.6/1.2_DP XMC-3E SB A,B. NE: 1. Reuse and re install exisitng 18G_0.6m at new place. 2. Reuse existing XMC-3E SB A,B. 3. Reuse exusting RTN910A. 4. Configure 18G_2+0_0.6/1.2_5 | MW SWAP A01073-A00607 WITH 18G_2+0_0.6/1.2_DP XMC-3E SB A,B. FE: 1. Reuse exisitng 18G_1.2m. 2. Reuse existing XMC-3E SB A,B. 3. Reuse exusting RTN910A. 4. Configure 18G_2+0_0.6/1.2_512QAM_EPLA. | [5 empty] | GCI | SQ202506180103-GCI | GCI | SQ202506160540-GCI | 2026-01-28 | 2026-01-30 | Completed | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | MUHAMMAD SYAFIQ BIN MUSTAFA6800000244 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1 | Unassigned | Completed |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | Ling/Tao6800000135 |  | GCI SCIENCE & TECHNOLOGY (MALAYSIA) SDN. BHD. | 1 | Unassigned | Completed |  | 2025-08-13 | 2025-08-20 | 2025-08-13 | 2025-08-13 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1 | Unassigned | Completed |  | 2026-01-21 | 2026-01-28 | 2026-01-21 | 2026-01-30 | MUDZLIAH//BINTI MUSTOPHA/6798000131 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1 | Assigned | Completed | Closed |  | DOWMY250911AU |  | 2025-09-12 | 2025-09-22 | Completed | 2025-09-11 | 2025-09-12 | 2025-09-11 | 2025-09-22 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1 | Assigned | Completed | [7 empty] | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-07-06 | Mohamad Wazir Bin Mohd TarmiziA0607607069848809495 | GCI TI | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | RAVIN//MUNISWARAN A/L MOHANADAS6800000087 |  |  | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-09-08 | Mohamad Wazir Bin Mohd TarmiziA0607607069848809495 | 2025-06-14 | 2025-06-28 | 2025-06-14 | 2025-09-08 | [6 empty] | 2025-09-19 | 2025-10-19 | 2025-09-19 | 2025-09-19 | NURUL//NADIA BINTI ABDULLAH/6800000045 | GTSB | SQ202505070167-GTSB | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | HSU//MYET CHAE/6799000011
3870C_HU | Hospital Serdang | DU00005283922 | Central | Selangor | 2.9766 | 101.7199 |  | 2026-04-25 |  | 2026-06-25 | DO | Pending PTW approval | ZTE | 00. Integrated/RFS Done | 21/4/2025 : UMOBILE - In-Building System - NE site 3870C Hospital Serdang, Digi OB - 60M 3 Legged Tower - FE site 1822B Mardi(ZED) | TSS+AA+TI+Dismantle | L1+ATP+MRCF+PAC | 2X RTN910 2X 23G 0.6M DP ANTENNA 1x ODU 23G XMC3E SUB A HI 1X ODU 23G XMC3E SUB A LO 1x ODU 23G XMC3E SUB B HI 1X ODU 23G XMC3E SUB B LO | MW Swap | MW SWAP LINK 3870C-1822B WITH HUAWEI_23G_2+0_0.6M/0.6M_DP_112MHZ_512QAM_1778MBPS_XMC3E_SUB_A & B_1.74KM IMPACTED: 3870C DISMANTLE EXISTING LIN | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. DISMANTLE EXISTING LINK | 1. INSTALL NEW IDU RTN910 2. INSTALL NEW 23G 0.6M DP ANTENNA 3. INSTALL NEW ODU 23G XMC3E 112MHZ SUB A & B 4. CONFIGURE LINK 23G 2+0 112MHZ 512QAM 5. PATCH TO NEW CP PORT AND DO PORT LAG 6. DISMANTLE EXISTING LINK | XMC3E | MAC | 23G | 0.6 | 0.6 | GTSB | SQ202505020369-GTSB | GTSB | SQ202504240805-GTSB // SQ202504240806-GTSB | 2025-11-25 | 2025-11-24 | Completed | 2025-07-24 | 2025-08-07 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1 | Assigned | Completed |  | 2025-07-24 | 2025-08-07 | 2025-07-24 | 2025-07-24 | MOHD//SHAHIDAN BIN SAFFINI/6799000114 | GTSB TI | Girobumi Technologies SDN. BHD. | 1 | Assigned | Completed |  | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-22 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1 | Assigned | Completed |  | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-24 | SITI NORHAFIQA BINTI AZMI6798000041 | Design and Material Team | ALL STAR ENGINEERING SDN. BHD. | 1 | Assigned | Completed | Closed |  | DOWMY25052161 |  | 2025-05-22 | 2025-05-27 | Completed | 2025-05-21 | 2025-05-22 | 2025-05-21 | 2025-05-27 | ZHANG DONG6000003031 | Warehouse Team | DCH Technology SDN.BHD | 1 | Assigned | Completed |  | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-10 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-10 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | GTSB TI | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | MOHD//AMIR BIN SAMSI/6799000184 |  | 2025-07-09 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-16 | KAMARUL NIZAM ASHBY BIN SEMAN6799000232 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-08 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | NG HONG JIE7018000036 | Logistic Team | 2025-11-20 | 2025-11-30 | 2025-11-20 | 2025-11-20 | NURFIKA//BINTI IBRAHIM/6237001402 | GCI_AA | SQ202510300160-GCI | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | EZRIN TASNIM BIN ABDUL GANI6798000128
7585A_HU | Sukau | DU00005283923 | Sabah | Sabah | 5.5202 | 118.2703 |  |  |  |  | Drop/Cancel |  |  | 00. Site Out/Drop |  |  |  |  | Cancel / Drop | [14 empty] | Not started | [8 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | [9 empty] | Unassigned | Not started | To be Submitted | [5 empty] | Not started | [8 empty] | Unassigned | Not started | [40 empty] | GTSB | SQ202506160769-GTSB